# Walk & Roll to School Day Timeline + Checklist

4–6 Weeks Before

- [ ] Pick event date

- [ ] Get administrator approval

- [ ] Recruit planning team (staff + parents + teacher)

- [ ] Reach out to local orgs for support (Food bank, TAMC, MCHD, Blue Zones, Ecology Action)

- [ ] Select 2–4 meeting spots/routes

- [ ] Assign volunteer leads for each route

3–4 Weeks Before

- [ ] Add event announcement to newsletter/website

- [ ] Send first email/text to families

- [ ] Distribute classroom announcement to teachers

- [ ] Gather materials (signs, stickers, incentives)

- [ ] Confirm any crossing or supervision needs

1–2 Weeks Before

- [ ] Post flyers/yard signs near school & send home individual flyers

- [ ] Remind families about “Park & Walk” option

- [ ] Confirm volunteer roles and meeting spot assignments

- [ ] Identify a photo volunteer (if allowed)

Week of Event

- [ ] Send final reminder to families

- [ ] Make schoolwide announcement

- [ ] Prepare supplies and route lists

Event Day

- [ ] Volunteers arrive early (10–15 minutes before meet time)

- [ ] Lead walking/biking groups from each meeting spot

- [ ] Greet students at the school entrance

- [ ] Celebrate participation (stickers, high-fives, photos)

After the Event

- [ ] Thank volunteers, families, teachers

- [ ] Share photos or highlights

- [ ] Recognize classrooms/participants

- [ ] Decide whether to schedule future Walk & Roll days